Statement of Work

Contract Number C-4600000791, Work Order WO01

Update to the Halfway Creek, Spring Creek, and South Branch of the Estero River, and Imperial River Region of the South Lee County Watershed Plan

- Introduction/Background

On February 14, 2008, the Governing Board of the South Florida Water Management District (District) approved permit number 36-03802-P for a project known as “I-75 Collier/Lee County Line North to Corkscrew Road/Segment B.” This permit authorized the widening of I-75 from four lanes to six lanes for this segment. As part of this permit, five 60-inch diameter culverts are proposed to be installed adjacent to two existing 9’ by 8’ box culverts at Station 431+95.18 (1.9 miles south of Corkscrew Road) to convey additional surface water flows from east of I-75 to the west. The additional culverts are proposed to accommodate a component of the South Lee County Watershed Plan (SLCWP). During the review of the permit application several concerns were expressed by adjacent property owners and other stakeholders in regard to the additional culverts proposed under I-75. To alleviate these concerns, Special Condition Number 14 was added to the permit that requires an update to the Halfway Creek, Spring Creek and South Branch of the Estero River region of the SLCWP to verify and validate the findings and material assumptions. The remainder of this section provides background for the SLCWP and particularly the Halfway Creek region.

In 1992 and 1995 a series of large rainfall events led to significant flooding in the Bonita Springs area, resulting in the evacuation and prolonged displacement of hundreds of citizens as well as associated flood damages to homes, businesses and public infrastructure.  As a result of flooding within the Imperial and Cocohatchee watersheds during these events, a study (SLCWP) was conducted to identify causes of the flooding, recommend improvements to the region, restore flowways, and prevent future flooding. The SLCWP was completed in July 1999 and identified a number of causes that contributed to the flooding. Most notably was the loss of historical flows within the Estero River and Halfway Creek watersheds.

The SLCWP identified the construction of I-75 as one of the causes of the loss of historical flows. The SLCWP also identified a number of improvements to be completed geared towards restoring natural flowways, removal of constrictions and enhancing conveyance capacities within Estero River, Imperial River, Cocohatchee River, Belle Meade and Camp Keais Strand.

- Scope of Work

The objective of this update is to verify and validate the findings and material assumptions of the SLCWP for the Halfway Creek, Spring Creek, and South Branch of the Estero River region. If conditions require revisions to the recommendations in the SLCWP then new recommendations are to be provided. The update should address and include:

- The required flow and conveyance capacity to restore flows to Halfway Creek, the South Branch of Estero River and Spring Creek.

- Identification of downstream impediments to the required flow.

- The model established under Phase I of the SLCWP: The Hydrologic – Hydraulic Model Development shall be reviewed for its accuracy to determine flow rates for “A” above based on changes to land uses and incorporation or implementation of any of the SLCWP elements since its completion. This shall also include validation of the computer models utilized in the SLCWP that would have any impact on “A” above.

- The ecological assessment performed under Phase II of the SLCWP shall be reviewed for its accuracy and relevance to current ecological goals, objectives and problems as identified in the latest Southwest Florida Feasibility Study draft work products.

- The problem identification and plan formulation developed under Phase III of the SLCWP shall be reviewed and updated to reflect work completed to date and any changes resulting from the review of Phase I and II above.

- Amendment No. 1 of the SLCWP shall be updated based on above findings including, but not limited to, verification of or recommended changes to flow distributions to receiving water bodies.

- Verification of upstream/inflow and downstream conveyance capacity.

- A control elevation, invert elevation, size, and number of culverts under I-75 shall be established based on the results of the above items and to avoid dewatering of upstream wetland systems east of I-75 and to ensure that the culverts do not cause or contribute to the County’s well field hydrological or water resource impacts. In addition, the upstream control elevations shall be based on the wet season water table information established from the County water table monitoring network and other available field identifiers until such time a wetland determination that established aerial extent, rim elevation and Uniform Mitigation Assessment Method (UMAM) scores for the property east of I-75 is completed and indicates otherwise.

Validation of the SLCWP shall include coordination with other regional studies such as the South West Florida Feasibility Study (SWFFS) and the Density Reduction Groundwater Resource (DRGR) Hydrologic/Hydraulic Study including modeling and study results. However, due to delays in the SWFFS, limited work products are available at this time. In addition, the new LIDAR topographic data for the DRGR Study is not yet available. Therefore, this scope does not include the Contractor’s use of the new LIDAR topographic data in the model due to schedule constraints.

The District and Lee County staff will be conducting periodic meetings with stakeholders to update them on the progress of this contract. These meetings may result in additional information that will be forwarded to the contractor. The Contractor will be asked to attend these meetings and present project updates.

- Work Breakdown Structure

Task I-A	Project Orientation

Boyle staff will attend a meeting with stakeholders, SFWMD and Lee County staff to identify and become familiar with problems and watershed management goals that initiated the SLCWP and review the background pertaining to this update of the SLCWP.

Task I-B	Data Collection

- Identify, review and compile data relevant to the development of an update to the SLCWP using data sources such as:

  - Previous hydrologic and hydraulic studies, as identified on Attachment A, conducted since the original SLCWP Study was completed in 1999.

  - SFWMD’s and Lee County’s GIS databases.

  - Information available from outside agencies such as NRCS, NWI, etc.

  - Recent data compiled for the Lee County Density Reduction Groundwater Resource Study.

- Review the array of subbasin studies for information regarding surface and groundwater flow characteristics of the region, including storm event modeling provided in existing or pending ERP files for projects identified by SFWMD as being located within the study area subbasins.

- Compile and review historical flow data and flow regime information for Halfway Creek, the South Branch of the Estero River, Spring Creek, and the Imperial River.

- Verify, through review of asbuilt drawings and permit records, the installed conveyance capacity from the culvert crossing under I-75 at Station 431+95.18 to the tidal waters of Halfway Creek, Spring Creek, and the South Branch of the Estero River.

- Identify the available format of data – electronic or other forms.

- Assess the availability of the information in SFWMD and Lee County’s GIS database, particularly topography, current land use/cover, soils, and locations of meteorological, surface and groundwater monitoring stations.

- Identify the prominent data gaps for potential future regeneration of missing records.

- Provide clear maps showing the location of data reference points with respect to roads and key hydraulic conveyance features.

Deliverables for Tasks I-A and I-B

Deliverable 1A: At 50% Progress or 4 weeks after the Notice to Proceed, Boyle will provide an email memorandum of progress on completed subtasks and preliminary findings.

Deliverable 1B: A memorandum or letter report on the available hydrologic/hydraulic and ecological information of the Halfway Creek, Spring Creek, South Branch of the Estero River, and Imperial River watershed, including:

- Description of surface water and groundwater hydrology

- Topography

- Existing land use

- Soils

- General geology

- Historical flow patterns

- Ecological Assessment data and goals

Information developed after completion of the SLCWP shall be noted in the memorandum.

The Contractor shall provide ten (10) copies of a draft memorandum within eight (8) weeks of the date of execution of the contract. Maps will be provided in digital format. The District and Lee County will review and request revisions within two (2) weeks of receipt of the deliverable. Twenty (20) copies of the final deliverable which incorporates the revisions requested by the District and Lee County are due within two (2) weeks from the receipt of the comments. An interim memo will document a 50% progress milestone four (4) weeks after the Notice to Proceed date of the Contract.

At this point in the implementation of the Work Order, scope, the time frames and deliverable payment amounts for the remaining tasks shall be negotiated based on the information collected. The negotiation shall be finalized in the form of a Work Order amendment. The time frames shall result in all deliverables being finalized on or before May 14, 2009.

STOP/GO POINT:  The Contractor shall stop work following completion of Task 1B to negotiate the timeframes and payment amounts for all remaining tasks. Said negotiations will be based on information collected in Task 1B. The Contractor is not authorized to proceed with Tasks 1C, II, III or IV until directed to do so by the District in the form of an executed Work Order Revision for all remaining tasks and deliverables. The Task and Deliverable descriptions set forth below are therefore not considered final until such time as a price for such work has been negotiated and agreed to by the District and a work order revision has been executed by both parties.

Task I-C	Survey Cross Sections and Model Update

Survey Cross Sections

The Contractor will provide surveying and mapping services for the field collection of ten (10) cross-sections as shown in width and location on the attached Exhibit A and one cross-section at the South Branch of the Estero crossing at Sanctuary Road as shown on Exhibit B. The surveying and mapping services shall meet all the requirements as set forth in “The Minimum Technical Standards” Chapter 61G17 Florida Administrative Code and shall include the following scope:

- The survey horizontal control shall be based on the Florida State Plane Coordinate System, and the vertical control shall be based on the North American Vertical Datum of 1988 (NAVD 88).

- The cross-sections shall be collected using geodetic positioning system (GPS) equipment to a horizontal and vertical positional tolerance of ±0.2’. All substantial changes in elevation shall be located as part of the cross-section.

- Two horizontal and vertical control points shall be established on site for future reference.

The Contractor will provide a Land Desktop Version 2007 AutoCAD file for engineering input into drainage models. No signed and sealed maps will be delivered for this task.

Model Update

The Contractor shall incorporate the new data, including the most complete information available on the Imperial River watershed, into a watershed hydrologic and hydraulic model of the SLCWP study area and calibrate the model. It is anticipated that the MIKE SHE/MIKE 11 model being calibrated by DHI, Inc. for the DRGR Study will be used for this modeling effort. That model includes the drainage area of the Estero River, Halfway Creek, Spring Creek, and Imperial River watersheds and will be able to handle interbasin transfers from the Estero to Imperial watersheds. This model will need additional details or represent the culverts, weirs and bridges in the Estero, Halfway, Spring and Imperial watersheds. At this point in time, approximately 42 structures need to be added to the model. The Task 1-B Data Collection memorandum provides details on those culverts, weirs and bridges.

The Contractor will add a new stream branch for the South Fork of Halfway Creek, and modifications shall be made for the eastern portions of the Estero River in the vicinity of I-75. The upper limit of Spring Creek tributaries shall be extended further upstream to represent the outflows from San Carlos Park. Cross sections will be obtained from existing hydraulic models of these systems or will be obtained from permit files.

Calibration data collected as part of Task 1-B from all watersheds within the study area (including the South Branch of the Estero, Halfway Creek, Spring Creek and Imperial River watershed) will be used to the greatest degree feasible (including Estero River N (DBKEYs 12806 and 12807), Estero River S (DBKEYs 12804 and 12805), Spring Creek (DBKEYs 12808 and 12809) and L-1691, L-1993, L-1994, L-1998, L-2194, L-5747, C-492, FP-1 through FP-12, ST1-ST3, and SF1-7 for periods when water levels were above the ground surface).   Calibration plots of flow will be provided in addition to the plots of stage for the Estero River, Spring Creek, and Imperial River. Flow and stage data are available for the Imperial River, Spring Creek, North Branch of the Estero River, and the South Branch of the Estero River from 1987 through 2006. Stage data is also available for Halfway Creek for 2007-2008 and the Kehl Canal gate on the Imperial River since 2003.

It is assumed that the model will be calibrated for wet season events during 2007 and August 2008. Validation will be performed for Tropical Storm Ernesto in September 2006. Additional groundwater extraction time series and rainfall data will be needed for 2007-2008 to accomplish this modeling update. It is assumed that Lee County will provide the public water supply well pumpage data and the grid rainfall data.

Calibration standards will be defined as part of the calibration document. If the calibration results deem modification of the model is warranted to increase its accuracy, it will be modified accordingly.

Attendance at two Stakeholder Meetings and site inspections to observe wet weather conditions are included in this Task.

Deliverables for Task I-C

A technical report shall be submitted describing the simulation algorithms and input data processing, calibration of the model, sensitivity analyses of simulation, problems encountered, and trouble shooting process during the calibration and verification process. Provide analytical and graphical summary of calibration results.

Ten (10) copies of a draft of the deliverable are due within 12 weeks of execution of the contract. The District and Lee County will review and request revisions within two (2) weeks of receipt of the deliverables, Twenty (20) copies of the final deliverable including revisions requested by the District and Lee County is due within two weeks from the receipt of the comments, An interim memo shall document a 50% progress milestone 8 weeks after the date of execution of the Contract.

Task II	Ecologic Assessment Update

The SLCWP ecological assessment shall be reviewed for its accuracy and relevance to current ecological goals, objectives and problems as identified in the latest Southwest Florida Feasibility Study draft work products. The assessment will consider normal wet season and dry season conditions. MIKE SHE/MIKE 11 modeling results will be used to generate hydroperiod maps for wetlands east of I-75. Time series plots of existing and proposed water depths for 10 locations west of I-75 will be provided to assist in the ecological assessment.

The Contractor’s hydroecological analysis will be limited essentially to two alternatives (no culverts and culverts under I-75), with gate elevations ultimately being set at whatever the model analyses indicates. The analysis will be limited to the roughly 2x1 mile "effect area" east of I-75; and no assessment of effects west of I-75 will be included. Field analyses will include 8-12 selected stations within the effect area where estimated current and target hydrologic regimes would be defined.  This is predicated upon surveyed NGVD benchmarks being available in close proximity to each of these stations (or upon NGVD elevations being provided later for Contractor-set benchmarks). Field evaluations will occur as soon as feasible to allow optimal interpretation of hydrobiological indicators before winter.

This task will not include a detailed UMAM/WRAP analyses, wetland delineations, or agency meetings. In addition, this task will not include a detailed assessment of potential effects on well fields or other areas outside the “effect area”.

Deliverables for Task II

The deliverable for Task II will be a written report describing the available hydrologic and ecological information of the DRGR Study Ecological Assessment draft work products, including descriptions of hydrology, general ecology, and historic hydrologic patterns and their interrelationships as they relate to habitat values. Differences between the SLCWP Ecologic Assessment and the DRGR Study Ecological Assessment shall be noted in the report. The report will describe effect area impacts related to the culvert installation and operation.

The Contractor shall provide ten (10) printed copies of a draft report within 24 weeks of the date of execution of the contract. District and Lee County staff will review and request revisions within two (2) weeks of receipt of the deliverable. The Contractor will provide twenty (20) printed copies and one (1) electronic copy of the final deliverable with revisions requested within two (2) weeks from the receipt of the comments. An interim memo shall document a 50% progress milestone 20 weeks after the date of execution of the Contract.

Task III	Problem Identification and Plan Formulation Update

The problem identification and plan formulation portion of the SLCWP shall be reviewed and updated to reflect work completed to date and any changes resulting from the previous deliverables.  The alternatives analysis for this Task will consist of a Base Condition, and up to four preferred alternatives. At this time it is anticipated that the alternatives will consist of:

- Five new culverts under I-75 at Halfway Creek.

- Two iterations on improved conveyance to Spring Creek and/or the South Branch of the Estero River.

- A detention alternative east of I-75.

The new culverts under I-75 may or may not be a part of the alternatives listed above under the second and third bullets. The presence or absence of additional culverts under I-75 is dependent on the predicted response of those additional culverts. If the additional culverts are predicted to cause flooding, then a modified approach would be appropriate, and could include either fewer culverts or culverts in different locations.

Attendance at one Stakeholder Meeting is included in this Task.

Deliverables for Task III

The deliverables for Task lII will include a detailed description of the findings on hydrologic-hydraulic performance of the existing water management facilities in the region. The hydrologic summary should describe the rainfall-runoff characteristics of each sub basin. Elaborate on the unique features of each sub basin such as the effect of basin storage, topography, land use, water tables, tailwater conditions, etc. on the overall rainfall-runoff process. Provide tabular and graphical summary of runoff hydrographs of the 5, 10, 25 and 100 year recurrence interval peak flows. The hydraulic summary should describe the performance of existing waterways and water control systems, stage-storage-discharge characteristics, and water surface profiles under the 5, 10, 25 and 100 year recurrence interval peak flow conditions. Differences in the problem identification and plan formulation of the SLCWP and the Task III deliverable shall be identified.

Ten (10) printed copies of a draft of Deliverable III are due within 25 weeks of execution of the contract. The District and Lee County will review and request revisions within three (3) weeks of receipt of the deliverable. Twenty (20) printed copies of the final deliverable including revisions requested are due within two (2) weeks from the receipt of the comments. An interim memo will document a 50% progress milestone 21 weeks after the date of execution of the Contract.

Task IV	Update to Amendment 1 and 2 of the SLCWP

Amendment 1 and Amendment 2 of the SLCWP shall be updated based on the findings of the previous tasks including: verification of or recommended changes to flow distributions to receiving water bodies; the required flow and conveyance capacity to restore flows to Halfway Creek, the South Branch of Estero River and Spring Creek; identification of downstream impediments to recommended flows; verification of upstream/inflow (1055 cfs which was permitted by the District for the Brooks development) and downstream conveyance capacity; and A control elevation for the culverts under I-75 shall be established to avoid dewatering of upstream wetland systems east of I-75 and to ensure that the culverts do not cause or contribute to the County’s well field hydrological or water resource impacts. In addition, the upstream control elevations shall be based on the wet season water table information established from the County water table monitoring network and other available field identifiers until such time a wetland determination that established aerial extent, rim elevation and Uniform Mitigation Assessment Method (UMAM) scores for the property east of I-75 is completed and indicates otherwise. A stakeholder meeting will be conducted to convey these results.

Deliverables for Task IV

The deliverable for Task IV will be a written report describing the portions of Amendment 1 of the SLCWP that have been verified, any recommended changes and the reasoning supporting the recommendations, and any additional information required under Task IV. Prior to finalizing the report the Contractor shall present the updated Amendment 1 at a stakeholder meeting to be arranged and advertised by the Contractor in coordination with the District and Lee County. The Contractor shall document public comment and summarize the meeting.

The Contractor shall provide ten (10) printed copies of a draft report within 30 weeks of the date of execution of the contract. District and Lee County staff will review and request revisions within two (2) weeks of receipt of the deliverable. The Contractor shall conduct a stakeholder meeting to present the updated Amendment 1 based on the draft report and comments from the District and Lee County. Documentation of the public comments and a summary of the meeting shall be submitted within one (1) week of the meeting.

The Contractor shall provide ten (10) printed copies of a revised draft report, if necessary based on the stakeholder meeting within 2 weeks of the meeting. District and Lee County staff will review and request revisions within one (1) week of receipt of the deliverable. The Contractor will provide twenty (20) printed copies and one (1) electronic copy of the final deliverable with revisions requested within one (1) week from the receipt of the comments. An interim memo shall document a 50% progress milestone 27 weeks after the date of execution of the Contract.

- Summary Schedule of Tasks and Deliverables

| Task | Deliverable | Description | Due Date from NTP | Amount ($) |
| --- | --- | --- | --- | --- |
| Task I | Deliverable IA & IB | Project Orientation and Data Collection | 50% Progress -4 wks Draft - 8 wks Final - 12 wks | $30,000 |
| Task I | Deliverable IC | Survey Cross Sections and Model Update | 50% Progress – 9 wks* Draft – 12 wks* Final – 16 wks* | $73,889 |
| Task II | Deliverable II | Ecologic Assessment Update | 50% Progress – 20 wks* Draft – 24 wks* Final – 28 wks | $33,108 |
| Task III | Deliverable III | Problem Identification & Plan Formulation Update | 50% Progress – 21 wks Draft – 25 wks* Final –27 wks* | $32,438 |
| Task IV | Deliverable IV | Update to Amendment 1 of the SLCWP | 50% Progress – 27 wks* Draft – 30 wks* Stakeholder Mtg – 31 wks* Revised Draft – 33 wks* Final – 34 wks* | $71,410 |
|  |  | Total Not-to-Exceed | $240,679 |

*Weeks from Phase 2 NTP date

Note: After completion of Deliverable IA and IB, the time frames and deliverable payment amounts for the remaining tasks shall be negotiated based on the information collected. The negotiation shall be finalized in the form of a contract amendment. The time frames shall result in all deliverables being finalized on or before May 14, 2009.

E.	Contractor Performance

The Contractor’s performance will be evaluated at the following frequencies:

- Interim

- Final

- Additional evaluations as determined by the Project Manager

A running average score of >/= 3.0 is required to maintain active status.

Attachment A

List of Documents to be Provided to Consultant

For Validation of South Lee County Watershed Plan

- Link to South Lee County Watershed Plan on Lee County’s Web site (provided)

- Copy of staff report with addendum for Permit No. 36-03802-P (I-75 Collier/Lee County Line North to Corkscrew Road/Segment B) issued February 14, 2008 (provided)

- Map of project region with SFWMD permit boundaries and permit numbers and pending permit application numbers (provided)

- Copy of cost share agreement between District and Lee County for this contract (provided)

- Information supporting the Southwest Florida Feasibility Study (District –limited information provided)

- Pursue electronic copy of SLCWP model (provided)

- Pursue electronic copy of any stormwater management system models of projects west of I-75 (provided)

- Scope of Work for DRGR Hydrologic/Hydraulic Study (provided)

- Topographic information to be used in the DRGR Study (provided)

- Any other data compiled for DRGR Study (provided)

- Access to Lee County’s water table monitoring network data (provided)